# Project Charter for an Offline Vaccine Cold Chain Monitoring and Alert System Pilot

## Project Title and Authorization

Project Title: Offline Vaccine Cold Chain Monitoring and Alert System Pilot

Date of Authorization: To be confirmed

Version: 1.0

Project Sponsor: Fatima Al-Sayed, Cold Chain Program Manager

## Purpose / Business Case

The organisation needs a more reliable way to monitor vaccine temperatures during last-mile delivery to rural clinics. The current process relies on paper strip-chart recorders that are checked manually by drivers and clinic staff. This approach has proved unreliable, and a recent incident resulted in vaccines being administered before a temperature excursion was identified.

The proposed pilot will introduce an offline-capable cold chain monitoring and alert system that can record temperature throughout the journey, provide local warnings without depending on internet connectivity, and keep reliable digital shipment records. The project also aims to reduce unnecessary vaccine wastage by giving qualified staff better information when deciding whether affected vaccines can still be used.

The project aligns with the organisation’s strategy by improving patient safety, strengthening cold chain accountability, supporting ministry and donor reporting, and testing a practical solution that could later be expanded to other rural delivery routes if the pilot is successful.

## Project Objectives and Success Criteria

The project will pursue the following objectives during the three-month pilot on the northern delivery route:

- Prevent undetected temperature excursions from reaching patients.

Success criterion: Zero undetected temperature excursions result in potentially affected vaccines being administered during the pilot.

- Maintain a complete temperature record for every pilot shipment.

Success criterion: Each shipment has a complete digital temperature history from depot departure to clinic handover, including the duration and extent of any temperature excursion.

- Provide reliable local alerts without depending on internet connectivity.

Success criterion: Drivers and clinic staff receive a clear local warning when a temperature problem occurs, including on parts of the route where internet or mobile coverage is unavailable.

- Evaluate whether the system is practical for wider use.

Success criterion: By the end of the pilot, the project team evaluates shipment records, detected incidents, device reliability, and feedback from drivers, nurses, and depot staff, and produces a recommendation on whether the system should proceed to wider rollout.

## High-Level Requirements

The project will provide the following high-level requirements during the pilot:

- Continuous temperature monitoring

The system must continuously record the temperature of each monitored vaccine cold box throughout the delivery journey.

- Offline local alerts

The system must provide a clear local warning when a temperature excursion occurs, without depending on internet or mobile connectivity.

- Simple status indication for users

Drivers and clinic staff should be able to understand the shipment status quickly, using a simple indication such as green for acceptable status and red for hold and seek advice.

- Support for vaccine-specific temperature rules

The system must support different temperature limits and exposure rules for different vaccine types, with changes restricted to authorised medical or pharmacy staff.

- Shipment and excursion records

The system must record key shipment information, including vaccine type, cold box, route, departure time, clinic stops, handover details, and any temperature excursion, including its duration and degree.

- Offline data storage and later synchronisation

Temperature and shipment records must be stored locally when connectivity is unavailable and synchronised when a connection becomes available.

- Basic reporting and audit records

Authorised staff should be able to review temperature histories, shipment records, incidents, and important changes such as updates to vaccine rules.

- User access and role control

Access to sensitive functions and records must be limited according to user roles and responsibilities.

- Reliable operation during a full delivery run

Monitoring devices must have sufficient battery capacity for the complete delivery journey and should be checked and prepared at the depot before use.

- Pilot backup procedure

Paper temperature logs must be retained as a temporary backup during the pilot in case of device failure.

## High-Level Project Description & Boundaries

The project will deliver a three-month pilot of an offline vaccine cold chain monitoring and alert system on the northern delivery route serving four clinics. The pilot will focus on detecting temperature problems during vaccine transport, providing clear local alerts without relying on internet connectivity, and maintaining reliable digital records for later review.

### In Scope

- Pilot deployment on the northern delivery route serving four clinics

- Continuous temperature monitoring for each monitored cold box

- Local offline alerts for drivers and clinic staff

- Simple status indication for nurses, such as green for acceptable status and red for hold and seek advice

- Support for different temperature rules for different vaccine types

- Recording of shipment details and temperature excursions

- Digital storage of temperature histories

- Synchronisation of records when connectivity becomes available

- Basic reporting for authorised staff

- User roles and controlled access

- Audit records for important changes

- User testing with drivers, depot staff and selected clinic nurses

- Basic training and user guidance

- Paper temperature logs retained as a temporary backup during the pilot

### Out of Scope

- Full rollout to all rural clinics

- Integration with national health information systems

- Predictive route optimisation

- Continuous GPS tracking of drivers

- Automatic clinical decisions on vaccine safety

- Development of certified medical-grade hardware from the ground up

- Large-scale installation across the full distribution network

- Advanced analytics or complex dashboards

### Expected Deliverables

- Working pilot prototype of the cold-box temperature monitoring and alert system

- Offline local alert function

- Digital temperature and shipment record system

- Basic reporting interface

- Vaccine-rule configuration and audit function

- Pilot deployment on the northern route

- User guidance and training materials

- Pilot test and evaluation report with findings and recommendations for possible wider rollout

## High-Level Risks

| Risk | Possible Impact | Mitigation |
| --- | --- | --- |
| Loss of internet or mobile connectivity | Alerts or data synchronisation may be delayed during rural deliveries. | Ensure local monitoring and alerts work offline, with data synchronised later. |
| Unreliable power supply | Devices may not be ready for use or may lose power during delivery. | Charge and check devices at the depot and use devices with enough battery for a full delivery run. |
| Device failure during transport | Temperature history may be lost and the shipment may become difficult to assess safely. | Retain paper logs as a backup during the pilot and record device failures for review. |
| False alerts | Staff may lose trust in the system or unnecessarily hold or discard usable vaccines. | Use vaccine-specific rules, test alert behaviour before deployment, and monitor false alerts during the pilot. |
| Missed temperature excursion | Potentially compromised vaccines could still reach patients. | Thoroughly test the monitoring devices before launch and treat missed excursions as a critical pilot failure. |
| Unclear response after an alert | A temperature problem may be detected but no one may know who should act. | Finalise the escalation and incident-response protocol before the pilot begins. |
| Outdated vaccine rules | Incorrect thresholds could lead to unsafe or unnecessary decisions. | Restrict rule changes to authorised medical or pharmacy staff and keep an audit record of changes. |
| Data governance issues | Unclear ownership, access, or retention may create legal or operational problems. | Prepare a data governance agreement before launch. |
| Unknown device certification requirements | Regulatory issues could delay deployment. | Confirm certification and regulatory requirements early in the project. |
| Scope creep | Additional features could delay the three-month pilot. | Keep the pilot limited to monitoring, local alerts, digital records, and basic reporting. |

## Summary Milestone Schedule

| Milestone | Target Time | Key Outcome |
| --- | --- | --- |
| Requirements and Approvals Completed | Weeks 1–2 | Pilot requirements, vaccine rules, incident-response process, data governance, certification requirements, and budget are confirmed. |
| Working Prototype Ready for Testing | Weeks 3–5 | Monitoring prototype, offline alerts, shipment records, vaccine-specific rules, and basic reporting functions are ready. |
| Pilot Approved for Field Use | Weeks 6–7 | System testing, user testing, training, and fallback procedures are completed. |
| Field Pilot Conducted | Weeks 8–11 | System is deployed on the northern route and pilot shipments, incidents, device failures, and user feedback are recorded. |
| Pilot Evaluation Report Completed | Week 12 | Pilot results are reviewed and a recommendation on possible wider rollout is prepared. |

## Summary Budget

The initial estimated budget for the three-month pilot is USD 42,000. The major cost categories are summarised below. These figures are planning estimates and should be confirmed before project approval.

| Cost Category | Estimated Cost (USD) |
| --- | --- |
| Temperature monitoring devices and spare units | $8,000 |
| Software development and configuration | $18,000 |
| Testing and pilot deployment | $5,000 |
| Training and user guidance | $2,000 |
| Initial technical support and maintenance | $3,000 |
| Data storage and backup | $1,000 |
| Compliance and technical review | $1,000 |
| Contingency | $4,000 |
| Estimated Initial Pilot Budget | $42,000 |

## Project Approval Requirements

| Requirement | Approval / Success Criterion | Responsible Approver |
| --- | --- | --- |
| Patient safety | Zero undetected temperature excursions result in potentially affected vaccines being administered during the pilot. | Project Sponsor, with clinical review |
| Temperature records | A complete digital temperature history is available for every pilot shipment. | Project Sponsor |
| Offline alert function | Local alerts operate without depending on internet or mobile connectivity. | Project Sponsor |
| Vaccine-specific rules | Temperature limits and exposure rules are reviewed and approved before field use. | Regional Pharmacist |
| Incident-response process | A clear response and escalation procedure is approved before the pilot begins. | Medical Director |
| Pilot readiness | Required testing, user preparation, fallback procedures, and regulatory checks are completed before field deployment. | Project Sponsor, with relevant clinical and technical reviewers |
| Pilot evaluation | An evaluation report is completed using shipment records, detected incidents, device reliability, and user feedback. | Project Sponsor |
| Wider rollout decision | Pilot findings are reviewed before any decision is made to extend the system beyond the northern route. | Project Sponsor, ministry and donor stakeholders |

The Regional Pharmacist must approve vaccine-specific temperature rules, while the Medical Director must approve the incident-response protocol before the system is used in the field. The Ministry Cold Chain Technical Advisor should review the pilot against ministry cold chain requirements before deployment. Overall pilot deliverables and completion will be reviewed by the Project Sponsor, the Cold Chain Program Manager.

## Assigned Project Manager and Authority Level

Project Manager: Pending formal appointment before project commencement

The Project Manager will be responsible for the day-to-day management of the pilot, including coordinating the development team, tracking progress, organising testing and deployment activities, managing routine project issues, and reporting progress to the Project Sponsor.

The Project Manager will have authority to:

- coordinate project tasks and team activities;

- manage the approved project schedule;

- organise testing, training, and pilot deployment activities;

- make routine operational decisions within the approved project scope;

- escalate major risks, delays, or issues to the Project Sponsor.

The Project Manager will not have independent authority to approve major changes to project scope, budget, clinical protocols, vaccine temperature rules, or ministry-related decisions. These matters must be escalated to the Project Sponsor or the relevant clinical authority.

## Key Stakeholders

| Stakeholder | Role | Involvement in the Project |
| --- | --- | --- |
| Cold Chain Program Manager | Project Sponsor | Oversees major decisions on scope, budget, stakeholder relationships, and reporting to the ministry and donors. |
| Project Manager | Day-to-day project management | Coordinates project activities, tracks progress, manages routine issues, and reports to the Project Sponsor. |
| Logistics Coordinator | Field coordination | Supports pilot planning, delivery operations, and coordination between the depot, drivers, and clinics. |
| Northern Depot Manager | Depot operations | Oversees shipment preparation, device checking, and operational readiness for the pilot route. |
| Drivers | Frontline transport users | Use the monitoring system during deliveries and respond to local alerts during transit. |
| Clinic Nurses | Receiving users | Check the shipment status before accepting vaccines and provide feedback on usability during the pilot. |
| Regional Pharmacist | Clinical and pharmacy authority | Approves vaccine-specific temperature rules and supports decisions when temperature excursions occur. |
| Medical Director | Clinical governance | Approves the incident-response protocol before pilot deployment. |
| Ministry Cold Chain Technical Advisor | Ministry oversight | Reviews the pilot against ministry cold chain requirements and is kept informed of progress. |
| Donor Partner | Funding stakeholder | Provides funding support and reviews pilot results when considering future support. |
| Local Health Authorities | Local oversight | Support coordination and any required approvals for clinics covered by the pilot route. |
| Legal Team | Data governance and compliance | Reviews issues related to data ownership, access, retention, and sensitive incident records. |
| Executive Director | Organisational oversight | Is briefed before pilot launch and provides senior-level organisational oversight. |

## Signatures (Authorization)

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | Fatima Al-Sayed, Cold Chain Program Manager | ____________ | ____________ |
| Project Manager | Pending formal appointment | ____________ | ____________ |