## Gantt Chart
VaxiFlow
| Project Start: |  | 2026-09-14
| Display Week: |  | 1 | 2026-09-14 | [6 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05
|  |  |  | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
TASK | START | DAYS | END | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1. Project Initiation & Planning
1.1 Defining Project Governance
1.1.1 Drafting and finalizing the project charter | 2026-09-14 | 2 | 2026-09-15
1.1.2 Confirming the final budget | 2026-09-16 | 2 | 2026-09-17
1.2 Establishing Compliance Frameworks
1.2.1 Reviewing medical device certification requirements | 2026-09-14 | 3 | 2026-09-16
1.2.2 Establishing baseline temperature rules | 2026-09-16 | 3 | 2026-09-18
2. Requirements Gathering & Analysis
2.1 Analyzing Software Requirements
2.1.1 Documenting user access levels & authentication criteria | 2026-09-16 | 2 | 2026-09-17
2.1.2 Defining shipment lifecycle, stops & handover | 2026-09-16 | 3 | 2026-09-18
2.1.3 Specifying local logging & delayed synchronization | 2026-09-19 | 3 | 2026-09-21
2.2 Analyzing Hardware Requirements
2.2.1 Defining sensor accuracy, power & calibration criteria | 2026-09-19 | 3 | 2026-09-21
2.2.2 Mapping LED trigger rules | 2026-09-22 | 2 | 2026-09-23
3. System Design & Architecture
3.1 Designing Software Architecture
3.1.1 Modeling edge storage & offline database schemas | 2026-09-22 | 3 | 2026-09-24
3.1.2 Designing UI wireframes | 2026-09-19 | 3 | 2026-09-21
3.1.3 Architecting delayed-sync queue | 2026-09-25 | 2 | 2026-09-26
3.2 Designing Hardware Configuration
3.2.1 Planning enclosure & physical device layout | 2026-09-22 | 3 | 2026-09-24
3.2.2 Designing charging & maintenance workflows | 2026-09-25 | 2 | 2026-09-26
4. System Development & Configuration
4.1 Sourcing & Configuring Hardware
4.1.1 Procuring sensors & offline hardware modules | 2026-09-25 | 7 | 2026-10-01
4.1.2 Assembling & calibrating prototype smart boxes | 2026-10-02 | 5 | 2026-10-06
4.2 Coding Core Software Modules
4.2.1 Developing authentication, user management & registries | 2026-09-22 | 7 | 2026-09-28
4.2.2 Implementing asset configuration registries | 2026-09-29 | 5 | 2026-10-03
4.3 Coding Logistical & Alert Engines
4.3.1 Developing shipment transit execution engine | 2026-09-22 | 7 | 2026-09-28
4.3.2 Programming offline excursion detection & audit logs | 2026-09-25 | 7 | 2026-10-01
4.3.3 Implementing delayed network synchronization | 2026-10-02 | 5 | 2026-10-06
4.4 Developing Reports & Analytics
4.4.1 Historical data extraction & incident dashboard | 2026-10-04 | 5 | 2026-10-08
4.4.2 Building exportable compliance reports | 2026-10-09 | 3 | 2026-10-11
5. Testing & Quality Assurance
5.1 Performing Internal Quality Engineering
5.1.1 Unit & integration testing | 2026-10-12 | 5 | 2026-10-16
5.1.2 Simulating extreme temperature excursions | 2026-10-07 | 3 | 2026-10-09
5.1.3 Testing offline data persistence | 2026-10-07 | 3 | 2026-10-09
5.2 Conducting User Acceptance Testing (UAT)
5.2.1 UAT with depot staff & delivery drivers | 2026-10-17 | 3 | 2026-10-19
5.2.2 On-site UAT with rural clinic nurses | 2026-10-17 | 3 | 2026-10-19
6. Implementation & Operational Readiness
6.1 Preparing Training & Field Logistics
6.1.1 Authoring user manuals & quick-reference guides | 2026-10-09 | 4 | 2026-10-12
6.1.2 Developing temporary paper-log SOP | 2026-10-17 | 2 | 2026-10-18
6.1.3 Conducting training workshops | 2026-10-20 | 3 | 2026-10-22
6.2 Deploying the Northern Route Pilot
6.2.1 Installing devices across 4 pilot clinics | 2026-10-20 | 3 | 2026-10-22
6.2.2 Launching live 3-month pilot | 2026-10-23 | 90 | 2027-01-20
7. Post-Pilot Evaluation & Closeout
7.1 Assessing Pilot Performance
7.1.1 Compiling shipment logs, incidents & uptime data | 2027-01-21 | 5 | 2027-01-25
7.1.2 Stakeholder interviews & surveys | 2027-01-21 | 5 | 2027-01-25
7.2 Project Finalization
7.2.1 Final pilot evaluation report | 2027-01-26 | 5 | 2027-01-30
7.2.2 Presentation to ministry & donor committees | 2027-01-31 | 1 | 2027-01-31

## Summarize
WBS | Activity | Start Date | End Date | Duration | Predecessor
1.1.1 | Drafting and finalizing the project charter | 2026-09-14 | 2026-09-15 | 2 days | —
1.1.2 | Coordinating with the finance team to confirm the final budget | 2026-09-16 | 2026-09-17 | 2 days | 1.1.1
1.2.1 | Reviewing and validating medical device certification requirements | 2026-09-14 | 2026-09-16 | 3 days | —
1.2.2 | Consulting clinical staff to establish baseline temperature rules | 2026-09-16 | 2026-09-18 | 3 days | 1.1.1
2.1.1 | Documenting user access levels and authentication criteria | 2026-09-16 | 2026-09-17 | 2 days | 1.1.1
2.1.2 | Defining shipment lifecycle states, stop management, and handover steps | 2026-09-16 | 2026-09-18 | 3 days | 1.1.1
2.1.3 | Specifying local data logging and delayed synchronization logic | 2026-09-19 | 2026-09-21 | 3 days | 2.1.2
2.2.1 | Defining sensor accuracy, power management, and calibration criteria | 2026-09-19 | 2026-09-21 | 3 days | 1.2.1, 1.2.2
2.2.2 | Mapping physical LED trigger rules | 2026-09-22 | 2026-09-23 | 2 days | 2.2.1
3.1.1 | Modeling local edge storage and offline-capable database schemas | 2026-09-22 | 2026-09-24 | 3 days | 2.1.3
3.1.2 | Designing UI wireframes for dashboards, registries, and reporting views | 2026-09-19 | 2026-09-21 | 3 days | 2.1.1, 2.1.2
3.1.3 | Architecting the queue system for delayed network data sync | 2026-09-25 | 2026-09-26 | 2 days | 2.1.3, 3.1.1
3.2.1 | Planning the enclosure setup and physical device layout inside cold boxes | 2026-09-22 | 2026-09-24 | 3 days | 2.2.1
3.2.2 | Designing charging and routine maintenance workflows | 2026-09-25 | 2026-09-26 | 2 days | 3.2.1
4.1.1 | Procuring smart monitoring sensors and offline hardware modules | 2026-09-25 | 2026-10-01 | 7 days | 2.2.1, 3.2.1
4.1.2 | Assembling and calibrating initial prototype smart boxes | 2026-10-02 | 2026-10-06 | 5 days | 4.1.1
4.2.1 | Developing authentication, user management, and contact registries | 2026-09-25 | 2026-10-01 | 7 days | 3.1.1, 3.1.2
4.2.2 | Implementing asset configuration registries | 2026-10-02 | 2026-10-06 | 5 days | 4.2.1, 3.1.1
4.3.1 | Developing the shipment transit execution engine | 2026-09-25 | 2026-10-01 | 7 days | 2.1.2, 3.1.1, 3.1.2
4.3.2 | Programming the local offline excursion detection algorithm and audit logs | 2026-09-25 | 2026-10-01 | 7 days | 2.2.2, 3.1.1
4.3.3 | Implementing delayed network queue data synchronization | 2026-10-02 | 2026-10-06 | 5 days | 3.1.3, 4.3.2
4.4.1 | Coding historical shipment data extraction and incident dashboard views | 2026-10-07 | 2026-10-11 | 5 days | 4.2.2, 4.3.1, 4.3.2, 4.3.3
4.4.2 | Building exportable compliance reports for ministry and donor review | 2026-10-12 | 2026-10-14 | 3 days | 4.4.1
5.1.1 | Executing unit and integration tests across hardware-software interfaces | 2026-10-15 | 2026-10-19 | 5 days | 4.1.2, 4.2.2, 4.3.1, 4.3.2, 4.3.3, 4.4.1, 4.4.2
5.1.2 | Simulating extreme temperature excursions to verify local offline alerts | 2026-10-07 | 2026-10-09 | 3 days | 4.1.2, 4.3.2
5.1.3 | Testing data persistence during forced, extended offline scenarios | 2026-10-07 | 2026-10-09 | 3 days | 4.1.2, 4.3.3
5.2.1 | Running UAT sessions with depot staff and delivery drivers | 2026-10-20 | 2026-10-22 | 3 days | 5.1.1, 5.1.2, 5.1.3
5.2.2 | Conducting on-site testing with rural clinic nurses using prototype indicators | 2026-10-20 | 2026-10-22 | 3 days | 5.1.1, 5.1.2, 5.1.3
6.1.1 | Authoring user manuals and physical quick-reference field guides | 2026-10-12 | 2026-10-16 | 5 days | 4.4.1
6.1.2 | Developing standard operating protocols for temporary paper logs | 2026-10-20 | 2026-10-21 | 2 days | 5.1.1
6.1.3 | Conducting training workshops for drivers, depot staff, and nurses | 2026-10-23 | 2026-10-25 | 3 days | 5.2.1, 5.2.2, 6.1.1, 6.1.2
6.2.1 | Physically provisioning and installing smart devices across the 4 pilot clinics | 2026-10-23 | 2026-10-25 | 3 days | 4.1.2, 5.2.2
6.2.2 | Launching the live 3-month pilot window | 2026-10-26 | 2027-01-23 | 90 days | 6.1.3, 6.2.1
7.1.1 | Compiling shipment logs, incident counts, and system uptime data | 2027-01-24 | 2027-01-28 | 5 days | 6.2.2
7.1.2 | Gathering qualitative feedback via stakeholder interviews and surveys | 2027-01-24 | 2027-01-28 | 5 days | 6.2.2
7.2.1 | Authoring the final pilot evaluation report and recommendations dossier | 2027-01-29 | 2027-02-02 | 5 days | 7.1.1, 7.1.2
7.2.2 | Presenting findings to the ministry and donor committees for rollout approval | 2027-02-03 | 2027-02-03 | 1 day | 7.2.1