Deliverable-Oriented Work Breakdown Structure

1. Project Management & Compliance (Core Lifecycle)

- 1.1 Project Initiation & Governance

  - 1.1.1 Project charter and stakeholder alignment

  - 1.1.2 Finance team budget confirmation

- 1.2 Regulatory Compliance & Certification

  - 1.2.1 Device certification requirement validation

  - 1.2.2 Clinical compliance sign-off for temperature rule structures

- 1.3 Pilot Evaluation & Reporting

  - 1.3.1 Pilot metrics tracking framework (shipment logs, incident counts)

  - 1.3.2 End-of-pilot stakeholder feedback collection (drivers, nurses, depot staff)

  - 1.3.3 Final pilot evaluation report & donor recommendation dossier

2. Hardware Procurement & Provisioning

- 2.1 Cold-Box Smart Monitoring Devices

  - 2.1.1 Smart monitoring sensor hardware sourcing

  - 2.1.2 Power management, charging, and calibration protocols

- 2.2 Offline Alert Hardware Components

  - 2.2.1 Local offline alert hardware modules

  - 2.2.2 Dual-color visual indicators configuration (Green/Red LED setups)

3. Software Architecture & Shared Infrastructure (Increment 1)

- 3.1 Core System Architecture

  - 3.1.1 Database schema design for offline storage and later synchronization

  - 3.1.2 Local edge data storage architecture for cold-box devices

- 3.2 Authentication & Access Control

  - 3.2.1 Multi-tier user management module (Depot staff, Drivers, Clinic nurses)

  - 3.2.2 Controlled access and secure login mechanism

- 3.3 Platform Management Dashboards

  - 3.3.1 Central administration dashboard interface

  - 3.3.2 Notification contact management registry

4. Vaccine Logistical Management Modules (Increment 2)

- 4.1 Asset Configuration Registries

  - 4.1.1 Vaccine box and unit asset management registry

  - 4.1.2 Physical cold box unit tracking profiles

- 4.2 Temperature Rule Engine

  - 4.2.1 Rule-based engine supporting multi-vaccine temperature thresholds

  - 4.2.2 Critical configuration audit log for vaccine rule modifications

5. Transit Execution & Offline Alert Core Engine (Increment 3)

- 5.1 Shipment Lifecycle Engine

  - 5.1.1 Shipment initialization module (Vaccine type, box ID, route selection)

  - 5.1.2 Delivery stop and northern route clinic location configuration

- 5.2 Temperature Monitoring & Offline Alert System

  - 5.2.1 Continuous temperature data-logging software engine

  - 5.2.2 Local offline excursion detection algorithm (Duration + Degree deviation calculation)

  - 5.2.3 Local hardware alert trigger (Green = Acceptable / Red = Hold & Advice)

- 5.3 Delivery Handover & Synchronization

  - 5.3.1 Clinic delivery stop handover and digital signature capture interface

  - 5.3.2 Shipment completion and termination pipeline

  - 5.3.3 Delayed network synchronization engine (Delayed-queue data transfer)

6. Reporting & Analytics Delivery (Increment 4)

- 6.1 Historical Auditing

  - 6.1.1 Digital temperature history extraction and archive module

  - 6.1.2 Excursion incident investigation reporting dashboard

- 6.2 Stakeholder Report Generation

  - 6.2.1 Basic reporting interface for depot managers and ministry stakeholders

  - 6.2.2 Exportable donor verification compliance sheets

7. Testing, Training, and Field Deployment (Final Increment)

- 7.1 Quality Assurance & User Testing

  - 7.1.1 End-to-end hardware-software integration testing

  - 7.1.2 User Acceptance Testing (UAT) with depot staff, drivers, and rural nurses

- 7.2 Operational Readiness & Deployment

  - 7.2.1 Standard operating procedures for temporary paper log backups

  - 7.2.2 Tailored end-user training materials and field guidance sheets

  - 7.2.3 Physical hardware setup and rollout across the 4 northern route clinics

Activity-Based Work Breakdown Structure (Phase-Based)

1. Project Initiation & Planning

- 1.1 Defining Project Governance

  - 1.1.1 Drafting and finalizing the project charter

  - 1.1.2 Coordinating with the finance team to confirm the final budget

- 1.2 Establishing Compliance Frameworks

  - 1.2.1 Reviewing and validating medical device certification requirements

  - 1.2.2 Consulting clinical staff to establish baseline temperature rules

2. Requirements Gathering & Analysis

- 2.1 Analyzing Software Requirements

  - 2.1.1 Documenting user access levels and authentication criteria

  - 2.1.2 Defining shipment lifecycle states, stop management, and handover steps

  - 2.1.3 Specifying local data logging and delayed synchronization logic

- 2.2 Analyzing Hardware Requirements

  - 2.2.1 Defining sensor accuracy, power management, and calibration criteria

  - 2.2.2 Mapping physical LED trigger rules (Green vs. Red alert behavior)

3. System Design & Architecture

- 3.1 Designing Software Architecture

  - 3.1.1 Modeling the local edge storage and offline-capable database schemas

  - 3.1.2 Designing UI wireframes for dashboards, registries, and reporting views

  - 3.1.3 Architecting the queue system for delayed network data sync

- 3.2 Designing Hardware Configuration

  - 3.2.1 Planning the enclosure setup and physical device layout inside cold boxes

  - 3.2.2 Designing charging and routine maintenance workflows

4. System Development & Configuration (Incremental Execution)

- 4.1 Sourcing & Configuring Hardware

  - 4.1.1 Procuring smart monitoring sensors and offline hardware modules

  - 4.1.2 Assembling and calibrating initial prototype smart boxes

- 4.2 Coding Core Software Modules

  - 4.2.1 Developing authentication, user management, and contact registries

  - 4.2.2 Implementing asset configuration registries (vaccine boxes, physical units)

- 4.3 Coding Logistical & Alert Engines

  - 4.3.1 Developing the shipment transit execution engine (departure, stops, handover)

  - 4.3.2 Programming the local offline excursion detection algorithm and audit logs

  - 4.3.3 Implementing delayed network queue data synchronization

- 4.4 Developing Reports & Analytics

  - 4.4.1 Coding historical shipment data extraction and incident dashboard views

  - 4.4.2 Building exportable compliance reports for ministry and donor review

5. Testing & Quality Assurance

- 5.1 Performing Internal Quality Engineering

  - 5.1.1 Executing unit and integration tests across hardware-software interfaces

  - 5.1.2 Simulating extreme temperature excursions to verify local offline alerts

  - 5.1.3 Testing data persistence during forced, extended offline scenarios

- 5.2 Conducting User Acceptance Testing (UAT)

  - 5.2.1 Running UAT sessions with depot staff and delivery drivers

  - 5.2.2 Conducting on-site testing with rural clinic nurses using prototype indicators

6. Implementation & Operational Readiness

- 6.1 Preparing Training & Field Logistics

  - 6.1.1 Authoring user manuals and physical quick-reference field guides

  - 6.1.2 Developing standard operating protocols for temporary paper logs

  - 6.1.3 Conducting training workshops for drivers, depot staff, and nurses

- 6.2 Deploying the Northern Route Pilot

  - 6.2.1 Physically provisioning and installing smart devices across the 4 pilot clinics

  - 6.2.2 Launching the live 3-month pilot window

7. Post-Pilot Evaluation & Closeout

- 7.1 Assessing Pilot Performance

  - 7.1.1 Compiling shipment logs, incident counts, and system uptime data

  - 7.1.2 Gathering qualitative feedback via stakeholder interviews and surveys

- 7.2 Project Finalization

  - 7.2.1 Authoring the final pilot evaluation report and recommendations dossier

  - 7.2.2 Presenting findings to the ministry and donor committees for rollout approval